## Outage and Maintenance
Transco 2025 Planned Outage and Maintenance Summary
This is a summary of the current Transco 2025 Pipeline Outage and Maintenance Projects. This document is subject to change to reflect the updated status of outage and maintenance projects.
[5 empty] | Updated on: | 2025-04-24
UWO | Job Number | Status | Start | Finish | Location | Zone | Maintenance Activity | Anticipated Impact | Meter No. | Meter Name | 1Line Nominatable Location ID | Job Specific Posting | Revision Notes
| 124452 | Outage Scheduled | 2025-04-23 | 2025-04-25 | TRANSCO STATION 17 - SINTON, TX | 1 | Compressor Station Outage/Annuals | Meters impacted listed | 4669 | Sinton | 9010299
| 124475 | Outage Scheduled | 2025-04-22 | 2025-04-22 | CORPUS CHRISTI MTR STA MS-4669 | 1 | Meter Station Outage | Meters impacted listed | 4669 | Sinton | 9010299
| 1081188 | Outage Scheduled | 2025-08-12 | 2025-08-15 | 26" MAINLINE A MAINA (10A100 to 10A110) | 1 | Line Outage | Possible impact to the availability of transportation services scheduled North to South. | 3680, 3515,4515, 1637, 3668,4668, 3676 | Pecan Verde, Banquete, King Ranch, Aqua Dulce, Whistler | 9013004, 9011580,9011581, 1008773, 9010418,9010419, 901190 | See job specific posting
| 27008 | Outage Scheduled | 2025-07-08 | 2025-07-09 | TRANSCO STATION 35 - HOUSTON, TX | 2 | Compressor Station Outage
| 285426 | Outage Scheduled | 2025-05-21 | 2025-05-21 | TRANSCO STATION 32 - WHARTON, TX | 2 | Compressor Station Outage | Meters impacted listed | 3667/4667 | Spanish Camp | 9009853/9009854
| 165836 | Outage Scheduled | 2025-07-15 | 2025-07-24 | 35A5 MLV REPLACEMENT | 2 | Line Outage | Possible impact to the availability of transportation services scheduled North to South and South to North. | 1626, 3249, 1628 | Crosscreek, Houston Bammel, Texaco Milton | 1005390, 1002699, 1006261
| 165845 | Outage Scheduled | 2025-07-15 | 2025-07-24 | DOT REPLACEMENT MAINLINE A MP 353.27 | 2 | Line Outage | Possible impact to the availability of transportation services scheduled North to South and South to North. | 1626, 3249, 1628 | Crosscreek, Houston Bammel, Texaco Milton | 1005390, 1002699, 1006261
| 1081200 | Dates to be determined |  |  | Mainline B (MLV 40B20 to Station 45) HS | 2 | Line Outage | Possible impact to the availability of transportation services scheduled North to South and South to North. | 3675 | Jasper | 9011000
| 1139052 | Outage Scheduled | 2025-06-23 | 2025-06-29 | TRANSCO STATION 42 - STARKS, LA | 2 | Main Unit 1 Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 1139873 | Outage Scheduled | 2025-06-23 | 2025-07-02 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Main Unit 1 Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 554300 | Outage Scheduled | 2025-07-10 | 2025-07-13 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Main Unit 2 Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 1139899 | Outage Scheduled | 2025-07-07 | 2025-07-09 | TRANSCO STATION 42 - STARKS, LA | 2 | Main Unit 2 Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 1140050 | Outage Scheduled | 2025-05-29 | 2025-05-29 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Station Outage ESD Test | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 1140068 | Outage Scheduled | 2025-05-29 | 2025-05-29 | TRANSCO STATION 42 - STARKS, LA | 2 | Station Outage ESD Test | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 1139078 | Outage Scheduled | 2025-07-07 | 2025-07-09 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Main Unit 2 Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 128979 | Outage Scheduled | 2025-05-30 | 2025-05-30 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Pipeline Inspection | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 255638 | Outage Scheduled | 2025-05-30 | 2025-05-30 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Pipeline Inspection | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 33862 | Outage Scheduled | 2025-04-22 | 2025-04-29 | STATION 54 COMPRESSOR STATION - WASHINGTON, LA | 3 | Compressor Station Outage | Operating Conditions resulting from this planned maintenance may require Transco to reduce the availability of injection quantities for WSS storage service during some of this maintenance period. |  |  |  | See job specific posting
| 933933 | Dates to be determined | 2025-12-01 | 2025-12-10 | 30"/36" MAINLINE B MAINB (60B20 to 65B1) | 3 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1008457 | Outage Scheduled | 2025-10-02 | 2025-10-20 | TRANSCO STATION 60 - JACKSON, LA | 3 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1008456 | Dates to be determined | 2025-08-11 | 2025-09-23 | TRANSCO STATION 50 - EUNICE, LA | 3 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 933926 | Outage Scheduled | 2025-03-25 09:00 | 2025-04-24 | TRANSCO STATION 45 - RAGLEY, LA | 3 | Compressor Station Outage | No impact anticipated
| 729455 | Dates to be determined | 2025-09-01 19:00 | 2025-09-08 19:00 | 36" MAINLINE C MAINC (MP 583.55 to MP 626.51) - 50C20 to 65C0 | 3 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 113157 | Outage Scheduled | 2025-05-05 | 2025-05-09 | TRANSCO STA 77 GAS STORAGE | 4 | Compressor Station Outage | Operating Conditions resulting from this planned maintenance may require Transco to reduce the availability of injection/withdrawal quantities for ESS storage service during some of this maintenance period. |  |  |  | See job specific posting
| 1008460 | Dates to be determined | 2025-11-23 | 2025-11-26 | TRANSCO STATION 65 - GREENSBURG, LA | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 153894 | Outage Scheduled | 2025-05-19 | 2025-06-06 | TRANSCO STATION 90 - SWEET WATER, AL | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. |  |  |  | See job specific posting
| 1075443 | Outage Scheduled | 2025-08-04 | 2025-08-16 | TRANSCO STATION 140 - MOORE, SC | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1075444 | Dates to be determined |  |  | 36' MAINLINE C MAINC (140C10 to 140C20) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 750789 | Outage Scheduled | 2025-06-03 | 2025-06-16 | TRANSCO STATION 120 - STOCKBRIDGE, GA | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 933938 | Outage Scheduled | 2025-04-22 | 2025-04-30 | TRANSCO STATION 110 - WADLEY, AL | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. |  |  |  | See job specific posting
| 1075438 | Dates to be determined | 2025-06-17 | 2025-06-30 | TRANSCO STATION 110 - WADLEY, AL | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 933936 | Dates to be determined |  |  | 42" MAINLINE D MAIND (84D20 to 90D10) | 4 | Line Outage | No impact anticipated
| 933937 | Dates to be determined |  |  | 42"/48" MAINLINE E MAINE (84E20 to 90E10) | 4 | Line Outage | No impact anticipated
| 1008459 | Dates to be determined |  |  | 36" MAINLINE C MAINC (65C0 to 65C10) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 933934 | Dates to be determined |  |  | 30"/36" MAINLINE B MAINB (65B1 to 65B10) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 933932 | Dates to be determined |  |  | 30" MAINLINE A MAINA (65A1 to 65A10) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1076732 | Outage Scheduled | 2025-05-13 | 2025-06-06 | 42" MAINLINE D MAIND (115D0 to 115D18) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1077891 | Outage Scheduled | 2025-09-12 | 2025-10-04 | 36" MAINLINE C MAINC (MP 1033.61 to MP 1077.06) | 4 | Pipe Replacement | Possible impact to the availability of transportation services scheduled South to North.
| 1077884 | Outage Scheduled | 2025-08-07 | 2025-09-09 | 36" MAINLINE B MAINB (120B0 to 125B10) | 4 | Pipe Replacement | Possible impact to the availability of transportation services scheduled South to North.
| 1077537 | Outage Scheduled | 2025-06-16 | 2025-08-04 | 30" MAINLINE A MAINA (MP 1033.61 to MP 1077.06) | 4 | Pipe Replacement | Possible impact to the availability of transportation services scheduled South to North.
| 249566 | Outage Scheduled | 2025-09-15 | 2025-09-29 | TRANSCO STATION 70 - TYLERTOWN, MS | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 29064 | Outage Scheduled | 2025-04-14 | 2025-04-17 | TRANSCO STATION 116 CS - OPERATING | 4 | Compressor Station Outage | Coordinated with customers. | 7416 | Smith Looper Bridge | 9009851
| 737885 | Outage Scheduled | 2025-05-06 | 2025-05-14 | TRANSCO STATION 115 - NEWNAN, GA MU1 | 4 | Main Unit Outage | Possible impact to the availability of transportation services scheduled South to North.
| 737886 | Outage Scheduled | 2025-04-21 | 2025-04-30 | TRANSCO STATION 115 - NEWNAN, GA MU2 | 4 | Main Unit Outage | Possible impact to the availability of transportation services scheduled South to North.
| 737888 | Outage Scheduled | 2025-05-15 | 2025-05-23 | TRANSCO STATION 115 - NEWNAN, GA MU3 | 4 | Main Unit Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1069271 | Outage Scheduled | 2025-04-18 07:00 | 2025-05-26 07:38 | TRANSCO STATION 110 - COMP UNIT 17 COMP-UNIT-17 | 4 | Main Unit Outage | Possible impact to the availability of transportation services scheduled South to North.
| 880760 | Outage Scheduled | 2025-05-06 | 2025-05-27 | TRANSCO STATION 115 - NEWNAN, GA | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1077537 | Outage Scheduled | 2025-06-08 | 2025-07-20 | 30" MAINLINE A MAINA (115A20 to 125A10) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1077891 | Outage Scheduled | 2025-08-28 | 2025-09-19 | 36" MAINLINE C MAINC (115C20 to 120C20) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1069269 | Outage Scheduled | 2025-03-07 07:00 | 2025-04-18 17:00 | TRANSCO STATION 110 - COMP UNIT 16 COMP-UNIT-16 | 4 | Main Unit Outage | Possible impact to the availability of transportation services scheduled South to North.
| 165785 | Outage Scheduled | 2025-10-02 | 2025-10-14 | TRANSCO STATION 140 - MOORE, SC | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 1013359 | Outage Scheduled | 2025-05-10 | 2025-05-26 | MAINLINE D MAIN D - 170-15 VLV SITE (MP 1472.72 to MP 1494.12) - 170D10 to V485 | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 43687 | Outage Scheduled | 2025-05-16 | 2025-07-01 | 30" MAINLINE A MAINA (MP 1326.11 to MP 1362.90) - 155A0 to 155A25 | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South. |  |  |  | See job specific posting | Finish date updated
| 909841 | Dates to be determined | 2025-07-10 | 2025-09-01 | 145-10 VLV SITE VS-145-10 (145B10 to 150B0) | 5 | Pipe Replacement | Possible impact to the availability of transportation services scheduled South to North.
| 1075448 | Outage Scheduled | 2025-06-02 | 2025-06-11 | TRANSCO STATION 170 CS | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 909850 | Outage Scheduled | 2025-06-04 | 2025-07-09 | 150-0 VLV SITE VS-150-0 (150B0 to 150B15) | 5 | Pipe Replacement | Possible impact to the availability of transportation services scheduled North to South. |  |  |  | See job specific posting
| 909843 | Outage Scheduled | 2025-04-29 | 2025-06-03 | 150-0 VLV SITE VS-150-0 (150A0 to 150A10) | 5 | Pipe Replacement | Possible impact to the availability of transportation services scheduled North to South.
| 909839 | Dates to be determined | 2025-09-02 | 2025-10-06 | 145-10 VLV SITE VS-145-10 (145A10 to 145A21) | 5 | Pipe Replacement | Possible impact to the availability of transportation services scheduled South to North.
| 1075452 | Outage Scheduled | 2025-04-29 | 2025-05-05 | TRANSCO STATION 185 - MANASSAS, VA | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 1077647 | Outage Complete | 2025-04-12 05:00 | 2025-04-23 | 30"/24" SOUTH VIRGINIA LAT B SVLB (MP 85.52 to 91.02) - VSB50 to VS251 | 5 | Line Outage | Meters impacted listed | 7407, 7412 | Brunswick, Greensville | 9008686, 9009329 | See job specific posting | Status, Finish date updated
| 205639 | Dates to be determined | 2025-05-20 | 2025-05-20 | CASCADE CREEK INTERCHANGE (IN) MTR STA MS-3587 | 5 | Meter Station Outage | Meters impacted listed | 3587 | Cascade Creek | 9001040
| 1077742 | Outage Scheduled | 2025-05-21 | 2025-05-23 | 20" SOUTH VIRGINIA LAT A SVL (93.66 to 102.90) - VSA60 to VSA70 | 5 | Line Outage | Meters impacted listed | 7262, 7264, 7341, 7274 | Emporia, Pleasant Hill, Conway, Ahoskie | 1003031, 1002730, 1003396, 1003395 | See job specific posting
| 148828 | Outage Scheduled | 2025-05-05 | 2025-05-26 | TRANSCO STATION 155 - LEXINTON, NC | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South. |  |  |  | See job specific posting | Finish date updated
| 148831 | Outage Scheduled | 2025-05-16 | 2025-05-26 | 30" MAINLINE A MAINA (150A20 to 155A4) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South. |  |  |  | See job specific posting | Dates updated
| 148835 | Outage Scheduled | 2025-05-06 | 2025-05-15 | 42" MAINLINE D MAIND (150D20 to 155D2) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South. |  |  |  | See job specific posting | Dates updated
| 89639 | Outage Scheduled | 2025-04-01 | 2025-05-01 | 30" LEIDY LINE A LEIDA (505LA11 to 505LA40) | 6 | Line Outage | Possible impact to the availability of transportation services West to East. |  |  |  | See job specific posting | Finish date updated
| 1097723 | Outage Scheduled | 2025-04-17 | 2025-05-03 | 36" MAINLINE C MAINC (195C0 to 195C10) | 6 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 1097703 | Outage Scheduled | 2025-05-04 | 2025-06-10 | 30" MAINLINE B MAINB (195B0 to 195BR6) | 6 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 351028 | Outage Scheduled | 2025-04-24 | 2025-05-08 | ELIZABETHTOWN CLOVERLEAF MTR STA MS-6017 | 6 | Anomaly Investigation | No impact anticipated | 6017 | Cloverleaf | 1006559
| 131407 | Dates to be determined | 2025-06-14 | 2025-08-09 | 30" MAINLINE A MAINA (195A0 to P499) - MP 1681 to MP 1715.08 | 6 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 26653 | Outage Scheduled | 2025-06-09 | 2025-06-23 | TRANSCO STATION 207 - PARLIN, NJ | 6 | Compressor Station Outage | Coordinated with customers.
| 1097714 | Dates to be determined | 2025-05-15 | 2025-06-15 | 36" MAINLINE CALDWELL B LOOP MLCWB | 6 | Anomaly Investigation | Possible impact to the availability of transportation services West to East.
| 249343 | Dates to be determined | 2025-09-08 | 2025-10-31 | NJN-VS-200A104 (R1 VALVE) | 6 | Line Outage | No meter impact anticipated
| 928446 | Dates to be determined | 2025-09-15 | 2025-10-22 | TRANSCO STATION 190 - ELLIOTT CITY, MD | 6 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 1075462 | Dates to be determined | 2025-11-05 | 2025-11-06 | TRANSCO STATION 200 - FRAZER, PA | 6 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 160115 | Dates to be determined | 2025-07-08 | 2025-09-30 | 30" MAINLINE A MAINA MP J706 to 200A40 (MP 1,771.00 to MP 1,794.70) | 6 | Line Outage | Impact being evaluated
| 160129 | Dates to be determined | 2025-07-08 | 2025-08-26 | 30" MAINLINE A MAINA MP 1,771.00 to MP 1,794.70 (MILLTOWN) | 6 | Line Outage | Impact being evaluated. Potential meter impact. | 6031, 6333, 6033 | Central, Edison, Sewaren | 1003319, 9008406, 1003320
| 131323 | Dates to be determined | 2025-07-14 | 2025-08-25 | 30" MAINLINE A MAIN A MP 1,747.93 (200A23 to 200A24) | 6 | Line Outage | Impact being evaluated
| 131402 | Dates to be determined | 2025-07-14 | 2025-08-04 | 30" MAINLINE B MAINB MP 1,747.93 (200B20 to 200B25) | 6 | Line Outage | Impact being evaluated
| 66228 | Dates to be determined | 2025-09-08 | 2025-10-31 | 30" MAINLINE A MAINA MP 1819.30 | 6 | Line Outage | Meters impacted listed. Possible impact to the availability of transportation services scheduled South to North. | 6039 | Harrison | 1003322
| 914415 | Outage Scheduled | 2025-05-05 | 2025-05-15 | TRANSCO STATION 515 - 42" PENN LEIDY LINE D LEIDD | 6 | REA | No impact anticipated
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Pipeline Inspection
Transco 2025 Planned Pipeline Inspection (ILI) Summary
This is a summary of the current Transco 2025 Pipeline Inspection Projects. This document is subject to change to reflect the updated status of ILI projects.
|  |  |  | Updated on: | 2025-04-24
UWO | Job Number | Status | Start | Finish | Location | Zone | Maintenance Activity | Anticipated Impact | Meter No. | Meter Name | 1Line Nominatable Location ID | Job Specific Posting | Revision Notes | Column1
| 1071403 | Outage Scheduled | 2025-04-15 | 2025-04-17 | 24" MCMULLEN LATERAL A MCMLA (MP 13.02 to MP 75.47) | 1 | Pipeline Inspection | No impact anticipated.
| 1071375 | Dates to be determined |  |  | 26" MAINLINE A MAINA ST30 to ST35 (MP 258.13 to MP 327.29) | 2 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 3641, 3667, 4667, 3607, 4607, 3096, 3679, 4653, 3568, 4510, 3559, 3545 | Glen Flora, Spanish Camp, Tres Wharton, Tejas, Matterhorn, Cross Creek, Katy Western Gas, Katy Enserch, White Oak Bayou | 1096690, 9006822, 9009853, 9009854, 9004066, 9004067, 9012943, 9007882, 1003164, 1003167, 1005518, 1001036
| 1071408 | Dates to be determined | 2025-08-26 | 2025-08-28 | 20" SOUTHWEST LOUISIANA (TEXAS GAS LOOP) LATERAL B SWLAB (MP 0 to MP 22.11) | 2 | Pipeline Inspection | System impact being evaluated.
| 1071407 | Dates to be determined | 2025-06-10 | 2025-06-24 | 36' MAINLINE B MAINB (MP 1124.73 to MP 1205.87) | 4 | Pipeline Inspection | No meter impact. Potential impact to transportation services from South to North.
| 1071406 | Dates to be determined |  |  | 30" SOUTHEAST LOUISIANA LATERAL (SELA) C SELAC (MP 101.77 to MP 130.84) | 3 | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071418 | Dates to be determined | 2025-10-07 | 2025-10-09 | 24" NORTH HI ISLAND LATERAL D NHILD (GATHERING) (MP 6.59 to MP 14.38) | 3 | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071389 | Dates to be determined |  |  | 30"/36" MAINLINE B MAINB (MP 467.99 to 517.24) | 3 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 2856 | ANR Duralde | 1005046
| 1071387 | Dates to be determined | 2025-08-05 | 2025-08-07 | 30"/36" MAINLINE B MAINB (MP 418.12 to MP 467.96) | 3 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 3554 | Enterprise Products | 1002337
| 1071388 | Dates to be determined |  |  | 30"/36" MAINLINE B MAINB (MP 583.64 to MP 626.48) | 3 | Pipeline Inspection | No meter impact. Potential impact to transportation services from South to North
| 1071378 | Dates to be determined |  |  | 30" MAINLINE A MAINA (MP 468.02 to MP 559.53) | 3 | Pipeline Inspection | No meter impact. Potential impact to transportation services from South to North.
| 1071398 | Dates to be determined |  |  | 30" MAINLINE A MAINA (MISSISSIPPI TO AMITE) | 3 | Pipeline Inspection | Possible impact to transportation services from South to North.
| 1071395 | Dates to be determined |  |  | 30" CAMERON PLANT LATERAL A CMPLA (Mp 0 to MP 20.27) | 3 | Pipeline Inspection | System impact being evaluated.
| 1071368 | Outage Scheduled | 2025-07-01 | 2025-07-10 | 42' MAINLINE E MAINE (MP 1124.74 to MP 1132.19) ST130 to ST140 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071367 | Outage Scheduled | 2025-08-12 | 2025-08-14 | 42"/48" MAINLINE E MAINE (MP 890.66 to MP 905.76) ST100 to ST110 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071414 | Outage Scheduled | 2025-08-19 | 2025-08-25 | 42' MAINLINE D MAIND (MP 1205.58 to MP 1212.53) ST140 to ST145 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071420 | Outage Scheduled | 2025-10-06 | 2025-10-24 | 42" MAINLINE D MAIND (MP 969.15 to MP 1048.32) ST100 to ST110 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071419 | Outage Scheduled | 2025-09-02 13:33 | 2025-09-18 13:33 | 36" MAINLINE C MAINC (MP 969.54 to MP 1048.35) ST110 to ST120 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071377 | Outage Scheduled | 2025-06-09 | 2025-06-24 | 30" MAINLINE A MAINA (MP 740.55 to MP 811.13) ST80 to ST90 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071379 | Outage Scheduled | 2025-07-15 | 2025-07-17 | 30" MAINLINE A MAINA (MP 890.61 to MP 909.87) ST100 to ST105 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071380 | Dates to be determined | 2025-06-03 | 2025-06-19 | 30" MAINLINE A MAINA (MP 1048.36 to MP 1124.7) - STA 120 to STA 130 | 4 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from South to North.
| 1071411 | Dates to be determined |  |  | 16" LATERAL LINE 456 PL-LL0456 (MP 0.01 to MP 1.78) | 4B | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071252 | Dates to be determined |  |  | 24" LATERAL LINE 450 PL-LL0450 (MP 34.16 to MP 60.73) | 4B | Pipeline Inspection | System impact being evaluated.
| 1071410 | Dates to be determined |  |  | 30" LATERAL LINE 400 PL-LL0400 (MP 0 to MP 6.66) | 4B | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071366 | Dates to be determined |  |  | 42" MAINLINE D MAIND (MP 1247.09 to MP 1261.82) - STA 145 to N545 | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071382 | Dates to be determined | 2025-07-15 | 2025-07-17 | 30" MAINLINE A MAINA (MP 1205.91 to MP 1247.03) - STA 140 to STA 145 | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071381 | Dates to be determined | 2025-05-06 | 2025-05-15 | 30" MAINLINE A MAINA (MP 1148.17 to MP 1154.74) - STA 130 to SAVANNAH RIVER | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071394 | Outage Scheduled | 2025-04-22 | 2025-04-24 | 24" CARDINAL LATERAL A CARD (MP 0 to MP 104.95) | 5 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 7369 | Iredell | 1003266
| 153798 | Dates to be determined | 2025-07-08 | 2025-07-22 | 36"/42" MAINLINE C MAINC (MP 1457.03 to MP 1521.81) - STA 170 to MLV 175C20 | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071392 | Dates to be determined | 2025-09-23 | 2025-10-07 | 36" MAINLINE C MAINC (MP 1394.61 to MP 1456.98) - MLV 160C15 to STA 170 | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071390 | Dates to be determined |  |  | 30"/36" MAINLINE B MAINB (MP 1247.12 to MP 1287.15) - STA 145 to STA 150 | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071417 | Dates to be determined | 2025-05-06 05:00 | 2025-05-09 12:00 | 30" MAINLINE A MAINA (MP 1494.33 to MP 1540.39) - JAMES RIVER TO STA 185 | 5 | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071397 | Dates to be determined | 2025-08-05 | 2025-08-07 | 10" MAIDEN LATERAL A MAIDA (MP 0 to MP 17.77) | 5 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 7318 | Lowesville | 1003245
| 1071415 | Outage Scheduled | 2025-03-04 | 2025-06-25 | 12" GROVER SC M&R LATERAL P7134 (MP 0 to MP 0.34) | 5 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 7134 | Grover | 1003398
| 1071416 | Dates to be determined | 2025-08-26 | 2025-08-28 | 20" WOODBRIDGE LATERAL WOODA (MP 0 to MP 2.4) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6331/6333 | Woodbridge | 9007765/9008406
| 1071399 | Dates to be determined | 2025-09-09 | 2025-09-12 | 12" WEST END LATERAL WENDA (MP 0.01 to MP 2.52) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be required. | 6236, 6230, 6043 | Kearny, Hudson Marion, West End | 9012223, 1003340, 1003323
| 1071404 | Dates to be determined | 2025-05-06 | 2025-05-09 | 8" WEST CONSHOHOCKEN LATERAL WCONA (MP 0 to MP 6.25) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6015 | West Conshohocken | 1003377
| 1071373 | Dates to be determined | 2025-05-06 | 2025-05-09 | TRENTON-WOODBURY B LATERAL TRWDB (MP 0 to MP 8.24) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6019, 6027, 6119, 6121 | Trenton, Hydro Research, Hamilton, Hamilton Mercer | 1003317, 1003318, 1003332, 1003333
| 1071400 | Dates to be determined | 2025-09-16 | 2025-09-19 | TRENTON-WOODBURY B LATERAL TRWDB (MP 8.21 to MP 26.13) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6297 | Burlington | 1003351
| 1071372 | Outage Scheduled | 2025-04-29 | 2025-05-01 | TRENTON-WOODBURY A LATERAL TRWDA (MP 0 to MP 26.07) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6019, 6027, 6119, 6121, 6297, 6309 | Trenton, Hydro Research, Hamilton, Hamilton Mercer, Fairless, Burlington | 1003317, 1003318, 1003332, 1003333, 1003351, 9000564
| 1071413 | Dates to be determined | 2025-08-04 | 2025-08-06 | 6" & 12" TRENTON LATERAL TRENA (MP 5.8 to MP 7.54) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6019, 6027 | Trenton, Hydro Research | 1003317, 1003318
| 1071412 | Dates to be determined | 2025-09-23 | 2025-09-26 | 6" POTTSTOWN LATERAL POTTA (MP 0 to MP 14.44) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6001, 6269 | Pottstown, Coventry | 1003373, 1007336
| 1071401 | Dates to be determined | 2025-05-20 | 2025-05-23 | 16" ORELAND LATERAL B ORLDB (MP 0.01 to MP 6.19) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6021, 6045, 6239 | Oreland, Ashmead Rd, Philadelphia Gas | 1003378, 1003460, 1003464
| 1071405 | Outage Scheduled | 2025-04-21 | 2025-04-25 | 12" MARCUS HK-WOODBURY A LATERAL MHWDA (MP 0 to MP 36.87) | 6 | Pipeline Inspection | No meter impact anticipated. Customer coordination may be required. |  |  |  |  | Finish date updated
| 1071371 | Dates to be determined | 2025-06-17 | 2025-06-20 | 20" MARCUS HK-WOODBURY B LATERAL MHWDB (MP 0.14 to MP 17.21) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6318 | Concord | 9001180
| 1071370 | Dates to be determined | 2025-06-24 | 2025-06-27 | 12" MARCUS HK-WOODBURY A LATERAL MHWDA (MP 0.12 to MP 19.14) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6318, 6041 | Concord, Wilmington | 9001180, 1003446
| 1071409 | Dates to be determined | 2025-08-12 | 2025-08-26 | 42" MAINLINE D MAIND (MP 1472.71 to MP 1494.07) - MLV 170D10 to JAMES RIVER | 5 | Pipeline Inspection | No meter impact anticipated. Possible impact to transportation services from North to South.
| 1071402 | Dates to be determined | 2025-08-19 | 2025-08-21 | 42" MAINLINE CALDWELL D LOOP MLCWD (MP 1789.65 to MP 1794.06) - STA 505 to MLV 505D05 | 6 | Pipeline Inspection | No meter impact anticipated. Evaluating system impact.
| 1071391 | Outage Scheduled | 2025-05-20 | 2025-05-22 | 42" MAINLINE C MAINC DELAWARE RIVER TO LOWER BAY LOOP C MORGAN M&R (MP 12.05 to MP 1765.65) | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6278, 6292, 6293, 6312 | Morgan, Sayreville NJN, Sayreville PSEG, Red Oak | 1006279, 1006292, 1003349, 1006312
| 1071374 | Dates to be determined |  |  | 30" MAINLINE A MAINA (MP 1770.97 to MP 1794.72) - TRENA to RARITAN RIVER | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6296 | Squibb Congen | 1003350
| 1071386 | Dates to be determined | 2025-07-08 | 2025-07-11 | 30" MAINLINE A MAINA (MP 1826.42 to MP 1831.45) - STA 240 to 134th ST | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6051 | Manhattan | 1003275
| 1071385 | Outage Scheduled | 2025-03-25 | 2025-03-27 | 30" MAINLINE A MAINA (MP 1722.26 to MP 1765.25) - STA 200 to DELAWARE RIVER | 6 | Pipeline Inspection | No impact anticipated.
| 1071384 | Outage Scheduled | 2025-04-22 05:00 | 2025-04-24 23:45 | 30" MAINLINE A MAINA (MP 1628.85 to MP 1674.49) - STA 190 to STA 195 | 6 | Pipeline Inspection | No meter impact. System impact being evaluated.
| 1071369 | Outage Scheduled | 2025-09-29 | 2025-09-30 | 42" LOWER BAY LOOP C MLLBC (MP 12.04 to MP 46.72) - MORGAN TO LONG BEACH | 6 | Pipeline Inspection | Meters impacted listed. Customer coordination may be needed. | 6278, 6210 | Morgan, Floyd Bennett, Long Beach | 1006279, 1003279
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0