## Copy To
Transco 2024 Planned Outage and Maintenance Summary
This is a summary of the current Transco 2024 Pipeline Outage and Maintenance Projects. This document is subject to change to reflect the updated status of outage and maintenance projects.
[5 empty] | Updated on: | 2024-04-16
UWO | Job Number | Status | Start | Outage Duration (Days) | Finish | Location | Zone | Maintenance Activity | Anticipated Impact | Meter No. | Meter Name | 1Line Nominatable Location ID | Revision Notes | Column1
| 394763 | Outage Scheduled | 2024-05-02 | 4 | 2024-05-05 | BRAZOS 538 PLATFORM BRZ-538-PL/Markham Plant Outage | 1 | Meter Station Outage | Meters impacted listed | 4626/3640, 4585, 3606/4606, 4473 1761/4618 4452 | Markham, Poole Road, Tres Mator, Wharton Dow, Perdido Markhan Valero | 9006162/9006642 9002300 9004063/9004064 1009506 9005165/9005164 1007155
| 951238 | Outage Scheduled | 2024-08-15 | 9 | 2024-08-23 | TRANSCO STATION 17 - SINTON, TX | 1 | Compressor Station Outage/Annuals | Possible impact to the availability of transportation services scheduled North to South.
| 951304 | Outage Scheduled | 2024-08-13 | 1 | 2024-08-13 | CORPUS CHRISTI MTR STA MS-4669 | 1 | Meter Station Outage | Meters impacted listed | 4669 | Sinton | 9010299
| 951264 | Outage Scheduled | 2024-04-14 | 9 | 2024-04-22 | TRANSCO STATION 23 - VICTORIA, TX | 1 | Compressor Station Outage/Annuals | Possible impact to the availability of transportation services scheduled North to South.
| 144027 | Outage Scheduled | 2024-08-13 | 10 | 2024-08-22 | 26" MAINLINE A MAINA (MP 341.53) | 2 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 800141 | Dates to be determined |  |  |  | TRES PALACIOS MTR STA MS-3607/4607 | 2 | Meter Station Outage | Meters impacted listed | 3607/4607 | Tres Palacios | 9004066/9004067
| 951201 | Dates to be determined |  |  |  | 26" MAINLINE A MAINA (MP 281.97) | 2 | Line Outage | Possible impact to the availability of transportation services scheduled North to South. Potential meter impact.
| 265065 | Outage Scheduled | 2024-04-08 | 30 | 2024-05-08 | LOUISIANA SOUTH DISTRICT PLATFORMS | 2 | Line Outage | Meters impacted listed | 2912 2482 2539 | SS 218 SS 229 SS 269 | 9007323 1007212 1006241
| 10939 | Outage Scheduled | 2024-06-04 | 7 | 2024-06-10 | TRANSCO STATION 42 - STARKS, LA | 2 | Compressor Station Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 11079 | Outage Scheduled | 2024-06-12 | 1 | 2024-06-12 | TRANSCO STATION 42 - STARKS, LA | 2 | Compressor Station Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 11034 | Outage Scheduled | 2024-06-06 | 5 | 2024-06-10 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Compressor Station Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 11069 | Outage Scheduled | 2024-06-12 | 1 | 2024-06-12 | TRANSCO STATION 44 - JOHNSON'S BAYOU, LA | 2 | Compressor Station Outage | Meters impacted listed | 4662 | Lighthouse Road | 9009310
| 123181 | Outage Scheduled | 2024-05-14 | 7 | 2024-05-20 | STATION 54 COMPRESSOR STATION - WASHINGTON, LA | 3 | Compressor Station Outage | Operating Conditions resulting from this planned maintenance may require Transco to reduce the availability of injection quantities for WSS storage service during some of this maintenance period.
| 949745 | Outage Scheduled | 2023-03-01 12:00 |  | 2024-04-19 | COMP UNIT 3 COMP-UNIT-3 | 3 | Main Unit Outage | Operating Conditions resulting from this planned maintenance may require Transco to reduce the availability of injection quantities for WSS storage service during some of this maintenance period.
| 40627 | Outage Scheduled | 2024-05-06 | 7 | 2024-05-12 | TRANSCO STATION 60 - JACKSON, LA | 3 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 481985 | Outage Scheduled | 2024-04-16 | 8 | 2024-04-23 | 30"/36" MAINLINE B MAINB (60B10 to 65B1) | 3 | Line Outage | Possible impact to the availability of transportation services scheduled South to North. Meters Impacted listed. | 4399 | Clinton | 1006831
| 19766 | Outage Scheduled | 2024-04-15 | 5 | 2024-04-19 | TRANSCO STATION 116 | 4 | Compressor Station Outage | No meter impact anticipated | 7416,7414,7418,7415,7421 | Smith Looper Bridge,Murray,Cartersville, Lucas Road,High Point | 9009851 9009613 9009809 9009610 9011080
| 162868 | Outage Scheduled | 2024-04-18 | 31 | 2024-05-19 | TRANSCO STATION 90 - MYRTLEWOOD, AL | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 162872 | Outage Scheduled | 2024-04-02 | 67 | 2024-06-08 | TRANSCO STATION 120 - STOCKBRIDGE, GA | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 162874 | Outage Scheduled | 2024-04-01 | 47 | 2024-05-18 | TRANSCO STATION 130 - COMER, GA | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 108926 | Outage Scheduled | 2024-05-20 | 14 | 2024-06-03 | TRANSCO STATION 100 - BILLINGSLEY, AL | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 185598 | Outage Scheduled | 2024-05-06 | 42 | 2024-06-17 | TRANSCO STATION 80 - SANDERVILLE, MS | 4 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled South to North.
| 162127 | Outage Scheduled | 2024-08-06 | 21 | 2024-08-27 | 42" MAINLINE D MAIND (105D10 - 105D20) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 61895 | Outage Scheduled | 2024-06-10 | 32 | 2024-07-12 | 36" MAINLINE C MAINC (120C0 -125C0) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 61892 | Outage Scheduled | 2024-07-16 | 33 | 2024-08-18 | 36" MAINLINE B MAINB (120B0 -125B0) | 4 | Line Outage | Possible impact to the availability of transportation services scheduled South to North.
| 647515 | Outage Scheduled | 2024-03-22 | 32 | 2024-04-22 | 36"/42" MAINLINE C MAINC (180C0 to 180C5) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 183484 | Outage Scheduled | 2024-04-01 | 35 | 2024-05-05 | TRANSCO STATION 160 - REIDSVILLE, NC | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South. See job specific notice.
| 162864 | Outage Scheduled | 2024-05-01 | 31 | 2024-05-31 | 16' TRYON SALES LATERAL TRYNA | 5 | Line Outage | No meter impact anticipated | 7225, 7227, 7221, 7326, 7229, 7294 | Mill Springs, Tryon, Inman, Landrum, Columbus, West Startex | 1003456, 1003457, 1003238, 1003169, 1003458, 1003244
| 22676 | Outage Scheduled | 2024-04-13 | 16 | 2024-04-28 | TRANSCO STATION 166 CS | 5 | Compressor Station Outage | No impact anticipated
| 33104 | Outage Scheduled | 2024-04-22 | 15 | 2024-05-06 | TRANSCO STATION 175 - SCOTTSVILLE, VA | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 333950 | Outage Scheduled | 2024-04-24 | 9 | 2024-05-02 | 24" CARDINAL LATERAL A CARD | 5 | Pipeline Maintenance | Potential meter impact | 7336, 7337 | Clayton PSNC, Clayton Piedmont | 2902980, 2902981
| 906387 | Outage Scheduled | 2024-05-06 | 26 | 2024-05-31 | TRANSCO STATION 150 - MOORESVILLE, NC. | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 22037 | Outage Scheduled | 2024-05-07 | 4 | 2024-05-10 | PLEASANT HILL MTR STA | 5 | Meter Station Outage | Meters impacted listed | 7264 | Pleasant Hill | 1002730
| 464441 | Outage Scheduled | 2024-05-13 | 5 | 2024-05-17 | TRANSCO STA 185 COMP | 5 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South.
| 22030 | Outage Scheduled | 2024-05-14 | 1 | 2024-05-15 | AHOSKIE MTR STA | 5 | Meter Station Outage | Meters impacted listed | 7274 | Ahoskie | 1003395
| 134536 | Outage Scheduled | 2024-05-21 | 2 | 2024-05-22 | IREDELL MTR STA MS-7369 | 5 | Line Outage | No meter impact anticipated | 7369-02 | Iredell | 1003266
| 557156 | Dates to be determined |  |  |  | 30" MAINLINE A MAINA (175A0 to 175A20) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 557169 | Dates to be determined |  |  |  | 30"/36" MAINLINE B MAINB (175B0 to 175B20) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 557180 | Dates to be determined |  |  |  | 36"/42" MAINLINE C MAINC (175C0 to 175C20) | 5 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 945704 | Outage Scheduled | 2024-04-15 | 7 | 2024-04-21 | TRANSCO STATION 515 - BEAR CREEK, PA - MAIN UNIT 6 | 6 | REA Main Unit Outage | Possible impact to the availability of transportation services scheduled West to East.
| 945705 | Outage Scheduled | 2024-04-22 | 9 | 2024-04-30 | TRANSCO STATION 515 - BEAR CREEK, PA - MAIN UNIT 7 | 6 | REA Main Unit Outage | Possible impact to the availability of transportation services scheduled West to East.
| 223298 | Outage Scheduled | 2024-04-22 | 12 | 2024-05-05 | TRANSCO STATION 515 - BEAR CREEK, PA | 6 | REA Compressor Station Outage | Possible impact to the availability of transportation services scheduled West to East.
| 41288 | Outage Completed | 2024-04-13 | 4 | 2024-04-15 | 24" FAIRLESS LATERAL FRLSA (J703 to J307) | 6 | Line Outage | Meters impacted listed. See job specific notice. | 6309 | Fairless | 9000564 | Status, Finish date updated
| 271362 | Outage Scheduled | 2024-04-13 | 9 | 2024-04-21 | TRANSCO STATION 535 - AUSTIN, PA | 6 | Compressor Station Outage | No impact anticipated
| 30361 | Outage Scheduled | 2024-04-16 | 8 | 2024-04-23 | 16" ALGONQUIN-CENT M&R LATERAL ALGNA | 6 | REA Meter Station Outage | Meters impacted listed. See job specific notice. | 4402 | Algonquin-Centerville | 1006561
| 945682 | Outage Scheduled | 2024-04-22 | 21 | 2024-05-12 | CENTERVILLE RGLTR STA (STA 505) | 6 | REA Regulator Station Outage | Possible impact to the availability of transportation services scheduled West to East. See job specific notice.
| 945686 | Outage Scheduled | 2024-04-22 | 33 | 2024-05-24 | 30" MAINLINE A MAINA (200A26 to 200A27) | 6 | REA Line Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 945687 | Outage Scheduled | 2024-04-22 | 33 | 2024-05-24 | 42" MAINLINE C MAINC (200C26 to 200C30) | 6 | REA Line Outage | Possible impact to the availability of transportation services scheduled South to North. See job specific notice.
| 63511 | Outage Scheduled | 2024-05-01 | 31 | 2024-05-31 | 8" ORELAND ASHMEAD EXTENSION A OREXA (P145/146 to P76) | 6 | Line Outage | Meters impacted listed | 6045 | Ashmead Road | 1006621
| 296907 | Outage Scheduled | 2024-05-01 | 12 | 2024-05-12 | 42" MAINLINE D MAIND (185D20 to 190D0) | 6 | Line Outage | Possible impact to the availability of transportation services scheduled North to South
| 815976 | Outage Scheduled | 2024-05-28 | 3 | 2024-05-30 | TRANSCO STATION 190 - ELLIOTT CITY, MD | 6 | Compressor Station Outage | Possible impact to the availability of transportation services scheduled North to South
| 41178 | Outage Scheduled | 2024-07-16 | 2 | 2024-07-19 | 30" MAINLINE A MAINA (MP 1795.00 to MP 1819.07) | 6 | Pipeline Inspection | Coordinating flow requirements with meter operators.
| 41180 | Outage Scheduled | 2024-08-06 | 5 | 2024-08-16 | 30" MAINLINE A MAINA (MP 1819.33 to 1826.43) | 6 | Pipeline Inspection | Coordinating flow requirements with meter operators.
| 41170 | Outage Scheduled | 2024-08-20 | 4 | 2024-08-29 | 36" MAINLINE CALDWELL B LOOP MLCWB (MP 1789.55 to MP 18020.65) | 6 | Pipeline Inspection | Coordinating flow requirements with meter operators.
| 704825 | Dates to be determined |  |  |  | 36"/42" MAINLINE C MAINC (185R7 to 190C0) | 6 | Line Outage | Possible impact to the availability of transportation services scheduled North to South.
| 249343 | Dates to be determined |  |  |  | 200A104 PIG TRAP VLV SITE VS-200A104 | 6 | Line Outage | Meters impacted listed | 6039 | Harrison | 1003322
| 248807 | Dates to be determined |  |  |  | 30" MAINLINE A MAINA (MP 1817.26 to MP 1817.60) | 6 | Line Outage | Meters impacted listed | 6327 | Clean Energy - Raymond | 9006942
| 249306 | Dates to be determined |  |  |  | 200A105 PIG TRAP VLV SITE VS-200A105 | 6 | Line Outage | Meters impacted listed | 6039 | Harrison | 1003322
| 41189 | Outage Scheduled | 2024-05-01 | 1 | 2024-05-03 | 16" PILES CREEK M&R LATERAL P6263 | 6 | Pipeline Inspection | Meters Impacted listed | 6263 | Piles Creek | 1007335
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0